## TPWODL
Planned Outages Report For the Month of MARCH 2022
From Date:- 01-03-2022 to 31-03-2022 OUTAGE REQUESTED ON ACCOUNT OF TPWODL
SL No- | Name of the Circle | Name of the Division | 220/132/33kV GSS Name | Name of the 33kV feeder | Date of Outage | Isolation Time | Restoration Time | Name of Outage taken Person | Affected Load in MW | Reason of Outage | Key Areas Affected | Remarks | PRESS NOTE RELEASE REQUIREMENT (YES/NO)
1 | BARGARH | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Melchamunda (Ghenss GSS to Melchamunda PSS) | 2022-03-02 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 6.7 | 5MVA PTR erection work | Melchamunda PSS remain shutdown | Outage from GSS | NO
2 | ROURKELA | RED,ROURKELA | 132/33KV CHHEND | 33KV KOLENAGAR | 2022-03-02 | 9:30 | 11:30 | SDO,KOLENAGAR | 8 | Tree Trimming | Kolenagar,Lindra,Jhirpani,Hamripur,Jagda |  | NO
3 | ROURKELA | RED,ROURKELA | 132/33KV CHHEND | 33KV NIT | 2022-03-02 | 9:30 | 11:30 | SDO,KOLENAGAR | 9 | Tree Trimming | NIT |  | NO
4 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV ROURKELA -2 | 2022-03-02 | 09.00 AM | 02.00 PM | SDO,RAJGANGPUR NO -I | 18 | MAINTENANCE WORK | INDUSTRIAL AREA | 33KV Line AB switch Maintenance/ Pin & Disc Insulators change | NO
5 | KALAHANDI | KWED | 33/11kV Dharamgarh PSS | Behera | 2022-03-02 | 9:00 | 14:00 | Mr. Bijay Mohapatra | 1 | Tree Trimming & PSS Maintenance | Behera, Parla, Chhanchanabahali | Only Behera PSS under Outage | NO
6 | SAMBALPUR | JED | Khandokata | kusumi | 2022-03-03 | 9:00 | 12:00 | SDO KUCHINDA | 0.1 | Tree trimming,Line Maintenance | kusumi |  | NO
7 | SAMBALPUR | SEED | Chiplima | HATIBARI | 2022-03-03 | 9:00 | 16:00 | SDO RAIRAKHOL | 4 | Tree trimming,Line Maintenance | hatibari,jujomura |  | NO
8 | BARGARH | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Katapali | 33KV Attabira | 2022-03-03 | 9:00 | 14:00 | Manmatha Nath Das (SDO of Attabira Sub-Division) | 22.6 | Insulator replacement work | Attabira,Patrapali,Thuapali and Bheden PSS remain shutdown. | Outage from GSS | NO
9 | ROURKELA | RSED,ROURKELA | 132/33KV ROURKELA | 33KV BONAI INDUSTRIAL | 2022-03-03 | 9:00 | 5:00 | SDO,PANPOSH | 19 | 3 Span(232sqmm) Condutor Restringing Near Lathikata | Industrial Area |  | NO
10 | KALAHANDI | KWED | 220/132/33kV Baner GSS | Ladugaon | 2022-03-03 | 10:00 | 14:30 | Mr. Deepak Ku. Sahoo | 0 | Line Maintenance | No Area under Outage | No PSS under Outage | NO
11 | KALAHANDI | NUAPADA | 33/11kV Khariar PSS | Sinapali | 2022-03-03 | 10:00 | 17:00 | Mr. Gagan Bihari Jena | 6 | VCB Installation & Oil Top-up in Sinapali PSS | Sinapali Town, Bargaon, Hatibandh, Kendumunda | Only Sinapali PSS under Outage | NO
12 | SAMBALPUR | JED | Khandokata | jamankira | 2022-03-04 | 9:00 | 12:00 | SDO KUCHINDA | 0.2 | Tree trimming,Line Maintenance | jamankira |  | NO
13 | BARGARH | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Tora | 2022-03-04 | 9:00 | 14:00 | Bijay Tiwary (SDO of Bargarh-2 Sub-Division) | 6 | Tree trimming work | 11KV Remunda,Tora,Sugarmill and Gaisima feeder | Outage from GSS | NO
14 | BARGARH | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Gaisilet | 2022-03-04 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 5.315 | Tree trimming work | Gaisilet,lebidi,firingimal,buromunda and talpali area | Outage from GSS | NO
15 | ROURKELA | RED,ROURKELA | 132/33KV CHHEND | 33KV BASANTI | 2022-03-04 | 9:00 | 2:00 | SDO,BASANTI | 0 | Tree Trimming | No Area Affected |  | NO
16 | ROURKELA | RSED,ROURKELA | 220/33KV BARKOT | 33KV MAHULIDIHA | 2022-03-04 | 8:00 | 12:00 | SDO,BONAI | 2 | Pin Insulator Replacement,Tree Trimming,V-Cross Arm Straighteening | Mahulidiha Section |  | NO
17 | ROURKELA | RED Rajgangpur | 132/33 KV KALUNGA | 33KV KALUNGA INDUSTRIAL | 2022-03-04 | 10.00 AM | 02.00 PM | SDO,KALUNGA | 8 | MAINTENANCE WORK AND TREE TRIMMING | KALUNGA INDUSTRIAL AREA | Pole Errection due low ground clearance and Maintenance work | NO
18 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV SUNDARGARH | 2022-03-04 | 9.00 AM | 05.00 PM | SDO,RAJGANGPUR NO -II | 6 | ERRECTION OF POLE AND MAINTENANCE WORK | KUTRA INDUSTRIES, ALANDA AREA | ELEPHANT CORRIDER WORK/ PIN INSULATOR CHANGE/ REJUMPERING/ ALANDA PSS MAINTENANCE WORK | NO
19 | KALAHANDI | KWED | 33/11kV Junagarh | Th. Rampur | 2022-03-04 | 9:00 | 14:30 | Mr. S. S.Swain | 1 | PSS Maintenance | Gopalpur, Th. Rampur, Badchhatarang, Dumerpadar | Only Th.Rampur PSS under Outage | NO
20 | SAMBALPUR | JED | Khandokata | kesibahal | 2022-03-05 | 9:00 | 12:00 | SDO KUCHINDA | 0.2 | Tree trimming,Line Maintenance | mahulpali |  | NO
21 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV KUTRA | 2022-03-05 | 9.00 AM | 05.00 PM | SDO,RAJGANGPUR NO -II | 14 | ERRECTION OF POLE AND MAINTENANCE WORK | KUTRA, INDUSTRIES | ELEPHANT CORRIDER WORK/ PIN INSULATOR CHANGE/ REJUMPERING/ KUTRA PSS MAINTENANCE WORK | NO
22 | ROURKELA | RED Rajgangpur | 132/33 KV CHHEND | 33KV ESTERN FDR (PART OF 33KV VEDVYAS) | 2022-03-05 | 10.00 AM | 02.00 PM | SDO,KALUNGA | 5 | MAINTENANCE WORK AND TREE TRIMMING | KALUNGA INDUSTRIALS | 33KV VCB Pole Assemble (limb) change/ Pin Insulator | NO
23 | KALAHANDI | KWED | 33/11kV Golamunda PSS | Kegaon | 2022-03-05 | 9:00 | 14:00 | Mr. Saroj Shukla | 2 | Line Maintenance & Tree Trimming | Kegaon, Lanji, Badchergaon | Only Kegaon PSS under Outage | NO
24 | KALAHANDI | KEED | 33/11kV M.Rampur | Banjamunda | 2022-03-05 | 10:00 | 19:00 | Mr. Deepak Ku. Behera | 1 | VCB Installation in Banjamunda PSS | Mohangiri, D.Karlakhunta | Only Banjamunda PSS under Outage | NO
25 | SAMBALPUR | JED | rajgangpur | Garposh | 2022-03-07 | 10:00 | 12:00 | SDO KUCHINDA | 0.1 | Tree trimming,Line Maintenance | town area |  | NO
26 | BARGARH | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Melchamunda (Melchamunda PSS to Kundakhai PSS) | 2022-03-07 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 2.8 | Mid span pole erection work | Kundakhai and Jamutpali area | Outage from GSS | NO
27 | ROURKELA | RED,ROURKELA | 132/33KV CHHEND | 33KV JAREIKALA | 2022-03-07 | 9:00 | 2:00 | SDO,BISRA | 0 | Tree Trimming | No Area Affected |  | NO
28 | ROURKELA | RED Rajgangpur | 132/33KV SUNDARGARH | 33KV BARGAON | 2022-03-07 | 09.00 AM | 03.00 PM | SDO,RAJGANGPUR NO -II | 14 | MAINTENANCE WORK AND TREE TRIMMING | JARANGLOI AND BARGAON | Jarongloi PSS and Bargaon PSS Maintenance/ Tree Trimming and Rejumpering | NO
29 | SAMBALPUR | JED | Khandokata | kusumi | 2022-03-08 | 9:00 | 12:00 | SDO KUCHINDA | 0.1 | Tree trimming,Line Maintenance | laida,kusumi |  | NO
30 | BARGARH | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Turunga | 2022-03-08 | 9:00 | 14:00 | Bijay Tiwary (SDO of Bargarh-2 Sub-Division) | 23.2 | Tree trimming and pin insulator replacing work at 33KV Turunga feeder | Turunga and Dasmile PSS remain shutdown | Outage from GSS | NO
31 | BARGARH | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Jharbandh to Dova) | 2022-03-08 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 2.6 | Tree trimming work | PSS Affected- Dova | Outage from Paikmal PSS | NO
32 | BARGARH | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Padampur GSS to Paikmal PSS) | 2022-03-09 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 19.6 | 33KV ISO's male contact replacement work at Jhankarpada(Near Padampur GSS) | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
33 | KALAHANDI | KWED | 33/11kV Charbahal | Badkutru | 2022-03-09 | 10:00 | 14:30 | Mr. S. S. Barik | 0 | Line Maintenance & Tree Trimming | No Area under Outage | No PSS under Outage | NO
34 | BARGARH | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Gaisilet | 2022-03-10 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 5.315 | PSS maintenance work | Gaisilet,lebidi,firingimal,buromunda and talpali area | Outage from GSS | NO
35 | BARGARH | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Melchamunda (Ghenss GSS to Melchamunda PSS) | 2022-03-11 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 7.9 | Tree trimming and maintenance work | Melchamunda and kundakhaiPSS remain shutdown | Outage from GSS | NO
36 | KALAHANDI | KWED | 33/11kV Junagarh | Th. Rampur | 2022-03-11 | 9:00 | 14:30 | Mr. S. S.Swain | 1 | PSS Maintenance | Gopalpur, Th. Rampur, Badchhatarang, Dumerpadar | Only Th.Rampur PSS under Outage | NO
37 | BARGARH | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Chiplima | 33KV Dhama-II (Dhatukpali to mahulpali) | 2022-03-12 | 9:00 | 14:00 | Pradipta Sarangi (SDO of Bheden Sub-division) | 22.8 | AB switch repairing work | Khuntulipali,Dhatukpali and Gondturum (Mahulpali) PSS remain shutdown. | Outage from GSS | NO
38 | BARGARH | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Katapali | 33KV Attabira | 2022-03-24 | 9:00 | 14:00 | Manmatha Nath Das (SDO of Attabira Sub-Division) | 22.6 | 33KV Saranda Isolator repairing work | Attabira,Patrapali,Thuapali and Bheden PSS remain shutdown. | Outage from GSS | NO
39 | BOLANGIR | Balangir | Sadeipalli | Madhiapalli | 05.03,2022 | 9:00 | 11:00 | SDO Balangir-2 | 1.5 | 33KV New Line Conductor Stringging at SadeiPalli Bypass | Madhiapalli,Sadeipalli Industrial,RE |  | NO
40 | BOLANGIR | Balangir | Laltikra | Dunguripalli | 07.03.2022 | 9:00 | 11:00 | SDO Balangir-2 | 8 | 33KV New Line Conductor Stringging at SadeiPalli Bypass | Pandkital,Cherupalli,Sargul,Dunguripalli |  | NO
41 | BOLANGIR | Balangir | Sonepur | Dumerbahal | 08.03.2022 | 9:00 | 12:00 | SDO -Sonepur | 2 | 11KV Breaker Installation in Charvata PSS | Balikhamar,Rengta,Charbhata |  | NO
42 | BOLANGIR | Sonepur | Sonepur | Dumerbahal | 14.03.2022 | 9:00 | 12:00 | SDO-Sonepur | 3.5 | 11KV Breaker Installation in Hardokhol PSS | Hardokhol Rural,Baidyanath,Bisimunda,Majhimunda,Khamsiripali |  | NO
43 | BOLANGIR | Sonepur | Sonepur | Sonepur | 14.03.2022 | 10:00 | 12:00 | SDO Sonepur | 4.5 | Linking of 33KV BMPUR Feeder and Sonepur Feeder | Badbazar,Collectorate,Hospital,Majhipada,Santinagar,Janmura-I,Hardokhol Urban |  | NO
44 | BOLANGIR | Sonepur | Sonepur | BMPUR | 15.03.2022 | 10:00 | 12:00 | SDO BMPUR | 12 | Linking of 33KV New Line from BMPUR Grid | Khandhota,Champapur,BMPur,Dharmasala,Jaloi,Subalaya,Structure,Telipali |  | NO
45 | BOLANGIR | Sonepur | Sonepur | BMPUR | 15.03.2022 | 10:00 | 12:00 | SDO BMPUR | 12 | Linking of 33KV New Line from BMPUR Grid | Khandhota,Champapur,BMPur,Dharmasala,Jaloi,Subalaya,Structure,Telipali |  | NO
46 | BOLANGIR | Balangir | Laltikra | Barpalli | 15.03.2022 | 9:00 | 11:00 | SDO Balangir-2 | 12 | 33KV New Line Conductor Stringging at Loisingha | Nagaon,Loisingha,Menda |  | NO
47 | BOLANGIR | Balangir | Laltikra | Dunguripalli | 18.03.2022 | 9:00 | 11:00 | SDO Balangir-2 | 8 | 33KV New Line Conductor Stringging at Fasad Village | Pandkital,Cherupalli,Sargul,Dunguripalli |  | NO
48 | BOLANGIR | Balangir | Laltikra | Barpalli | 19.03.2022 | 9:00 | 11:00 | SDO Balangir-2 | 12 | 33KV New Line Conductor Stringging at Chattamakhna PSS | Sujia,Kusumel,Chuibandha,Chattamakhna,Kharmunda |  | NO
49 | BOLANGIR | Balangir | Sadeipalli | Madhiapalli | 21.03.2022 | 9:00 | 11:00 | SDO Balangir-2 | 1.5 | 33KV New Line Conductor Stringging at SadeiPalli Bypass | Madhiapalli,Sadeipalli Industrial,RE |  | NO
50 | BOLANGIR | Balangir | Laltikra | Barpalli | 22.03.2022 | 9:00 | 11:00 | SDO Balangir-2 | 12 | Erection of 4 Pole Structure at Loisingha | Nagaon,Loisingha,Menda |  | NO

## Master (hidden)
Circle | Circle | Division | SAMBALPUR | ROURKELA | KALAHANDI | BOLANGIR | BARGARH | Start Date | End Date | Start Time | End Time
SAMBALPUR | SAMBALPUR | SED | SED | RED RKL | KEED | BED,Bolangir | BED, Bargarh | 2021-01-01 | 2030-12-31 | 0:00 | 24:00 PM
ROURKELA | SAMBALPUR | SEED | SEED | RSED RKL | KWED | TED, Titilagarh | BWED, Bargarh
KALAHANDI | SAMBALPUR | JED, Jharsuguda | JED, Jharsuguda | RED Rajgangpur | NUAPADA | SED,SONEPUR
BOLANGIR | SAMBALPUR | BNED Brajrajnagar | BNED Brajrajnagar | SED
BARGARH | SAMBALPUR | DEOGARH | DEOGARH
| ROURKELA | RED RKL
| ROURKELA | RSED RKL
| ROURKELA | RED Rajgangpur
| ROURKELA | SED
| KALAHANDI | KEED
| KALAHANDI | KWED
| KALAHANDI | NUAPADA
| BOLANGIR | BED,Bolangir
| BOLANGIR | TED, Titilagarh
| BOLANGIR | SED,SONEPUR
| BARGARH | BED, Bargarh
| BARGARH | BWED, Bargarh

## OPTCL
Planned Outages Report For the Month of MARCH 2022
From Date:- 01.03.2022 to 31.03.2022 OUTAGE REQUESTED ON ACCOUNT OF OPTCL
SL No. | Name of the Circle | Name of the Division | 220/132/33 KV GSS Name | Name of 33 KV O/G Feeder or Name of Equipment | Date of Outage | Isolation Time | Restoration Time | Name of Outage taken Person | Affected Load in MW | Reason of Outage | Key Areas Affected | Remarks | PRESS NOTE RELEASE REQUIREMENT (YES/NO)