## TPWODL
Planned Outages Report For the Month of Oct 2021
From Date:- 01.10.2021 to 31.10.2021 OUTAGE REQUESTED ON ACCOUNT OF TPWODL
SL No. | Name of the Circle | Name of the Division | 220/132/33kV GSS Name | Name of the 33kV feeder | Date of Outage | Isolation Time | Restoration Time | Name of Outage taken Person | Affected Load in MW | Reason of Outage | Key Areas Affected | Remarks | PRESS NOTE RELEASE REQUIREMENT (YES/NO)
1 | Kalahandi | NED | Khariar | 33kV Khariar 1 Feeder (Chalna- Sinapali) | 2021-10-02 | 9AM | 1PM | Mr. Gagan Bihari Jena | 2 | Tree Trimming & Maintenance | Sinapali, Hatibandh, Kendumunda |  | NO
2 | Kalahandi | KEED | Kesinga | 33kV Kesinga Feeder | 2021-10-04 | 9AM | 12AM | Mr. Surya Kanta Pusti | 10 | Tree Trimming | Kesinga Town, Boringpadar, Jaganathpur, Durga Rice Mill |  | NO
3 | Kalahandi | KEED | Bhawanipatna | 33kV Town 2 (Attanguda) Feeder | 2021-10-04 | 9AM | 1PM | Mr. Binayak Rout | 2.5 | Tree Trimming & Maintenance | Saidham, Jugsaipatna, Kruguda, Sagada |  | NO
4 | Kalahandi | KEED | Kesinga | 33kV Narla Feeder | 2021-10-05 | 8AM | 2PM | Mr. Deepak Ku. Behera | 14.5 | Tree Trimming & Railway Crossing work | Narla, M.Rampur, Lanjigarh & Karlamunda Block |  | NO
5 | Kalahandi | KEED | Bhawanipatna | 33kV Town 2 Feeder | 2021-10-06 | 9AM | 2PM | Mr. Debi Prasad Dixit | 11 | Tree Trimming & Maintenance | No.1 , No. 2 & Medical area |  | NO
6 | Kalahandi | KWED | Junagarh | 33kV Dharamgarh Feeder (Behera) | 2021-10-06 | 9AM | 10AM | Mr. Bhagaban Sahu | 2 | Tree Trimming & Maintenance | Behera, Parla, Chanchanbahali |  | NO
7 | Kalahandi | KWED | Junagarh | 33kV Dharamgarh Feeder (Behera) | 2021-10-06 | 2PM | 3PM | Mr. Bhagaban Sahu | 2 | Tree Trimming & Maintenance | Behera, Parla, Chanchanbahali |  | NO
8 | Kalahandi | NED | Khariar | 33kV Komna Feeder | 2021-10-06 | 8AM | 1PM | Mr. Bholanath Nayak | 9 | Tree Trimming & Maintenance | Komna, Bargaon, Komna, Kurumpuri, Batibahal |  | NO
9 | Kalahandi | KEED | Kesinga | 33kV Bhawanipatna 1 Feeder | 2021-10-07 | 9AM | 12PM | Mr. Binayak Rout | 1.5 | Tree Trimming & Maintenance | Karlapada, Marding, Cheliamal, Chagaon |  | NO
10 | Kalahandi | KWED | Junagarh | 33kV Daspur Feeder | 2021-10-07 | 9AM | 2PM | Mr. Bhagaban Sahu | 2 | Tree Trimming & Maintenance | Daspur, Brundabahal, Kumari, Farang |  | NO
11 | Kalahandi | KEED | Kesinga | 33kV Narla Feeder (Madanpur) | 2021-10-08 | 8AM | 1PM | Mr. Deepak Ku. Behera | 2 | Tree Trimming | Mohangiri, Manikera, D. Karlakhunta, Madanpur, Singhpur GP |  | NO
12 | Kalahandi | NED | Khariar | 33kV Khariar 1 & 2 Feeder | 2021-10-09 | 9AM | 1PM | Mr. Gagan Bihari Jena | 27 | Tree Trimming & Maintenance | Chalna, Sinapali, Sindheikela, Borda, Badi, Khariar Town |  | NO
13 | Kalahandi | NED | Khariar | 33kV Khariar 1 Feeder (Sinapli feeder) | 2021-10-16 | 9AM | 1PM | Mr. Gagan Bihari Jena | 7 | Tree Trimming & Maintenance | Chalna, Sinapali, |  | NO
14 | Kalahandi | KEED | Kesinga | 33kV Bhawanipatna 1 Feeder | 2021-10-16 | 9AM | 4PM | Mr. Susant Ku. Behera | 3 | Tree Trimming & Maintenance | Utkela, Kundabandh, Pastikudi |  | NO
15 | Kalahandi | KEED | Kesinga | 33kV Narla Feeder (Biswanathpur) | 2021-10-17 | 8AM | 1PM | Mr. Deepak Ku. Behera | 4 | Tree Trimming & Maintenance | Lanjigarh Block |  | NO
16 | Kalahandi | KEED | Kesinga | 33kV Belgaon Feeder | 2021-10-19 | 9AM | 2PM | Mr. Amiya Ranjan Panda | 5 | Tree Trimming | Karlamunda, Nunmath, Sisakhal |  | NO
17 | Kalahandi | NED | Khariar | 33kV Boden Feeder | 2021-10-23 | 9AM | 2PM | Mr. Gagan Bihari Jena | 2 | Tree Trimming & Maintenance | Timanpur, Gorla, Nilji, Babebir |  | NO
18 | Bargarh | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Chiplima | 33KV Dhama-II (Chiplima GSS to Khuntlipali PSS) | 2021-10-01 | 9:00 | 14:00 | Banchha Nidhi Naik (SDO of Bheden Sub-division) | 22.8 | Re-jumpering and tree trimming work at Dhama-II feeder | Khuntulipali,Dhatukpali and Gondturum (Mahulpali) PSS remain shutdown. | Outage from GSS | NO
19 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Paikmal PSS to Jharbandh PSS) | 2021-10-01 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 11.5 | Tree trimming work | PSS Affected-Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
20 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Lakhmara | 2021-10-02 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 3.048 | Tree trimming and pin insulator replacement work | Sambalpuri and Badikata area | Outage from GSS | NO
21 | Bargarh | Bargarh West Electrical Division (BWED) | Barpali 132/33KV GSS | 33KV Sarandapali | 2021-10-02 | 8:00 | 12:00 | Guru Charan Sahu (SDO of Barpali Sub-Division) | 10.4786 | Re-jumpering and tree trimming work | Sarandapali,Banbaspali,S.Dumerpali and Kantapali | Outage from GSS | NO
22 | Bargarh | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Turunga | 2021-10-03 | 9:00 | 14:00 | Anant Kumar Sahu (SDO of Bargarh-2 Sub-Division) | 23.2 | Tree trimming and pin insulator replacing work at 33KV Turunga feeder | Turunga and Dasmile PSS remain shutdown | Outage from GSS | NO
23 | Bargarh | Bargarh West Electrical Division (BWED) | Barpali 132/33KV GSS | 33KV Sarandapali | 2021-10-03 | 8:00 | 12:00 | Guru Charan Sahu (SDO of Barpali Sub-Division) | 10.4786 | Re-jumpering and tree trimming work | Sarandapali,Banbaspali,S.Dumerpali and Kantapali | Outage from GSS | NO
24 | Bargarh | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Dungri (Ganga cut point to Dungri PSS) | 2021-10-04 | 9:00 | 14:00 | Subrat Ku. Seth (SDO of Bhatli Sub-division) | 2.5 | Tree trimming work | Dungri PSS remain shutdown. | Outage from GSS | NO
25 | Bargarh | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Sohela | 2021-10-04 | 9:00 | 14:00 | Adikanda Das (SDO of Sohela Sub-Division) | 23.4721 | Tree trimming and pin insulator replacement work | Sohella Town,Chhuriapali ,Luhurachati, Industrial,Grinjal,Kangaon and Padampur Feeder | Outage from GSS | NO
26 | Bargarh | Bargarh West Electrical Division (BWED) | Barpali 132/33KV GSS | 33KV Melchamunda (Barpali GSS to Charmunda PSS) | 2021-10-04 | 9:00 | 14:00 | Guru Charan Sahu (SDO of Barpali Sub-Division) | 4.8583 | Tree trimming and pin insulator replacement work | Agalpur,Tinkani and Sujia | Outage from GSS | NO
27 | Bargarh | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Dungri (Ganga cut point to Dungri PSS) | 2021-10-05 | 9:00 | 14:00 | Subrat Ku. Seth (SDO of Bhatli Sub-division) | 2.5 | Tree trimming work | Dungri PSS remain shutdown. | Outage from GSS | NO
28 | Bargarh | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Katapali | 33KV Attabira | 2021-10-05 | 9:00 | 14:00 | Bijay Behera (SDO of Attabira Sub-Division) | 22.6 | 33KV Disc insulator replacement work near Sarada | Attabira,Patrapali,Thuapali and Bheden PSS remain shutdown. | Outage from GSS | NO
29 | Bargarh | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Melchamunda (Melchamunda PSS to Kundakhai PSS) | 2021-10-05 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 2.8 | Tree trimming and pin insulator replacing work | Kundakhai and Jamutpali area | Outage from GSS | NO
30 | Bargarh | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Bijepur | 2021-10-05 | 9:00 | 14:00 | Adikanda Das (SDO of Sohela Sub-Division) | 18.9 | 33KV AB switch maintenance and tree trimming | Barmunda,Bijepur town,Sarandapali,Jaring ,Kharmunda,Laumunda,Jokhipali and Saipali area | Outage from GSS | NO
31 | Bargarh | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Dungri (Bhatli PSS to Bhukta PSS) | 2021-10-08 | 9:00 | 14:00 | Subrat Ku. Seth (SDO of Bhatli Sub-division) | 6.8 | Tree trimming work | All 04Nos PSS name Bhukta,Ambabhona,Kandpala and Dungri PSS remain shutdown. | Outage from GSS | NO
32 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Padampur GSS to Paikmal PSS) | 2021-10-08 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 19.6 | Tree trimming work | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
33 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Paikmal PSS to Mandosil PSS) | 2021-10-08 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 3.5 | Tree trimming work | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
34 | Bargarh | Bargarh West Electrical Division (BWED) | Barpali 132/33KV GSS | 33KV Pandkital | 2021-10-08 | 9:00 | 14:00 | Guru Charan Sahu (SDO of Barpali Sub-Division) | 8.192 | Tree trimming work | Tulundi and Resam | Outage from GSS | NO
35 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Dahita | 2021-10-11 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 2.286 | Tree trimming and pin insulator replacement work | Siletpali,jamartala and dangachhancha area | Outage from GSS | NO
36 | Bargarh | Bargarh West Electrical Division (BWED) | Ghenss 132/33KV GSS | 33KV Melchamunda (Melchamunda PSS to Kundakhai PSS) | 2021-10-17 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 2.8 | Tree trimming and pin insulator replacing work | Kundakhai and Jamutpali area | Outage from GSS | NO
37 | Bargarh | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Dungri (Bhatli PSS to Bhukta PSS) | 2021-10-18 | 9:00 | 14:00 | Subrat Ku. Seth (SDO of Bhatli Sub-division) | 6.8 | Tree trimming work | All 04Nos PSS name Bhukta,Ambabhona,Kandpala and Dungri PSS remain shutdown. | Outage from GSS | NO
38 | Bargarh | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Katapali | 33KV Attabira | 2021-10-18 | 9:00 | 14:00 | Bijay Behera (SDO of Attabira Sub-Division) | 22.6 | Tree trimming work | Attabira,Patrapali,Thuapali and Bheden PSS remain shutdown. | Outage from GSS | NO
39 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Paikmal PSS to Jharbandh PSS) | 2021-10-18 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 11.5 | Tree trimming work | PSS Affected-Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
40 | Bargarh | Bargarh Electrical Division (BED) | 132 / 33 KV GSS Chiplima | 33KV Dhama-II (Chiplima GSS to Khuntlipali PSS) | 2021-10-21 | 9:00 | 14:00 | Banchha Nidhi Naik (SDO of Bheden Sub-division) | 22.8 | Re-jumpering and tree trimming work at Dhama-II feeder | Khuntulipali,Dhatukpali and Gondturum (Mahulpali) PSS remain shutdown. | Outage from GSS | NO
41 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Jharbandh PSS to Dova) | 2021-10-25 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 6.5 | Tree trimming work | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Jharbandh PSS | NO
42 | Bargarh | Bargarh Electrical Division (BED) | Pradhanpali 132/33KV GSS | 33KV Dungri (Bhatli PSS to Bhukta PSS) | 2021-10-26 | 9:00 | 14:00 | Subrat Ku. Seth (SDO of Bhatli Sub-division) | 6.8 | Tree trimming work | All 04Nos PSS name Bhukta,Ambabhona,Kandpala and Dungri PSS remain shutdown. | Outage from GSS | NO
43 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Padampur GSS to Paikmal PSS) | 2021-10-27 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 19.6 | Tree trimming work | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
44 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Lakhmara | 2021-10-29 | 9:00 | 14:00 | Sujit Behera (SDO of Padampur Sub-Division) | 3.048 | Tree trimming and pin insulator replacement work | Sambalpuri and Badikata area | Outage from GSS | NO
45 | Bargarh | Bargarh West Electrical Division (BWED) | Padampur 132/33KV GSS | 33KV Paikmal (Jharbandh PSS to Dungripali) | 2021-10-30 | 9:00 | 14:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 3.5 | Tree trimming work | PSS Affected-Dungripali | Outage from Jharbandh PSS | NO
46 | Balangir | Balangir | 132/33 KV Laltikra(Old Balangir) | Dunguripalli | 03.10.2021 | 8:00 | 12:00 | Mr.kamlesh Pradhan(SDO-1 Balangir) | 8 | Tree Trimming | Shankar Rice MILL Premises |  | NO
47 | Balangir | Balangir | 132/33 KV Laltikra(Old Balangir) | Dunguripalli | 10.10.2021 | 8:00 | 12:00 | Mr.kamlesh Pradhan(SDO-1Balangir) | 8 | Tree Trimming | Swosti Ecowares Premises |  | NO
48 | Balangir | Balangir | 132/33 KV Laltikra(Old Balangir) | Chudapalli | 17.10.2021 | 08:00 | 12:00 | Mr.kamlesh Pradhan(SDO-2Balangir) | 8 | Tree Trimming | Lower Suktel Dam |  | NO
49 | Balangir | Balangir | 132/33 KV Laltikra(Old Balangir) | Titlagarh | 05.10.21 | 9:00 | 13:00 | Mr.kamlesh Pradh1an(SDO-Balangir) | 11 | Tree Trimming,Pin insulator Change | Balangir Town,Industrial Areas |  | NO
50 | Balangir | Balangir | 132/33 KV Laltikra(Old Balangir) | Boudh Feeder-Link to Govt.Medical | 31.10.2021 | 09:00 | 13:00 | Mr.kamlesh Pradhan(SDO-1Balangir) | 10 | Tree Trimming,V cross Arm Straightening | Balangir Town |  | NO
51 | Balangir | Balangir | 132/33 KV Laltikra(Old Balangir) | Barpalli | 12.10.2021 | 9:00 | 13:00 | Mr.kamlesh Pradhan(SDO-1Balangir) | 12 | Tree Trimmin,Ground Clerance work Job |  |  | NO
52 | Balangir | Titlagarh | 132/33KV Kantabanji | Industrial Feeder | 2021-10-04 | 8:00 | 12:00 | Mr.AbaniKant Moharana(SDO-Kantabanji) |  | Tree Trimming | Industrial Area |  | NO
53 | Balangir | Titlagarh | 33/11KV Belgaon | Saintala Link Line | 2021-10-02 | 8:00 | 12:00 | Mr.Nursingha Nanda Prustry(SDO-Saintala) | 3.5 | Bend pole rectification,AB Switch Rectification,Pin Insulator replacement | Badi,Bhadra,Bijepur |  | NO
54 | Balangir | Titlagarh | 132/33KV Kesinga | Kesinga-Belgaon | 2021-10-11 | 8:00 | 12:00 | Mr.Nursingha Nanda Prustry(SDO-Saintala) |  | Intermediate Pole erection | Badi,Bhadra,Bijepur |  | NO
55 | Balangir | Titlagarh | 33/11KV belgaon PSS | Belgaon-Spaw paper Industry | 2021-10-15 | 8:00 | 12:00 | Mr.Nursingha Nanda Prustry(SDO-Saintala) | 3.5 | AB Switch,Pin Insulator Replace | Spaw Paper Industry |  | NO
56 | Balangir | Titlagarh | 132/33KV Rampur | Belpada | 2021-10-08 | 8:00 | 12:00 | Mr.Ram Chandra Meher(SDO-Patnagarh) | 4 | AB Switch,Insulator RepairTree Trimming | Kahapani,Nuhand,Padampur,Mandal,Ghanguli,Navoday |  | NO
57 | Balangir | Titlagarh | 132/33KV Rampur | Khaprakhol-Lathore | 2021-10-15 | 8:00 | 12:00 | Mr.Ram Chandra Meher(SDO-Patnagarh) |  | AB Switch Repair,Insulator,Tree Trimming |  |  | NO
58 | Balangir | Titlagarh | 132/33KV Rampur | Patntagarh-Khaprakhol | 2021-10-20 | 8:00 | 12:00 | Mr.Ram Chandra Meher(SDO-Patnagarh) | 12 | AB Switch Repair |  |  | NO
59 | Sambalpur | SED | Ganesh Nagar | Cheruapada | 2021-10-09 | 9 | 14 | Mr.Ranjit Gaya Sdo Khetrajpur | 12 | Line and PSS Maintenance | Cheruapada,Badbazar,PHED,Big bazar |  | No
60 | Sambalpur | SED | Ganesh Nagar | Cheruapada | 2021-10-16 | 9 | 14 | Mr.Ranjit Gaya Sdo Khetrajpur | 12 | Line and PSS Maintenance | Cheruapada,Badbazar,PHED,Big bazar |  | No
61 | Sambalpur | SED | Ganesh Nagar | Cheruapada | 2021-10-23 | 9 | 14 | Mr.Ranjit Gaya Sdo Khetrajpur | 12 | Line and PSS Maintenance | Cheruapada,Badbazar,PHED,Big bazar |  | No
62 | Sambalpur | SED | Kantapali | Burla,Burla Medical | 2021-10-08 | 9 | 14 | Mr. Somnath Seth SDO Burla | 12 | Line and PSS Maintenance | Burla,burla medical,Hirakud |  | No
63 | Sambalpur | SEED | Rairakhol | Rairakhol | 2021-10-04 | 7 | 14 | Mr. Deepak Raut SDO Rairakhol | 3 | Line extension for NH Crossing | Rairakhol |  | No
64 | Sambalpur | SEED | Rairakhol | Naktideoul | 2021-10-04 | 7 | 14 | Mr. Deepak Raut SDO Rairakhol | 3 | Line extension for NH Crossing | Naktideoul,Kisinda |  | No
65 | Sambalpur | BNED | Remja-1 | TRL-2 | 2021-10-05 | 9 | 15 | Mr.Kandu Toppo SDO Belpahar | 2 | Line and PSS Maintenance | Jharuapada |  | No
66 | Sambalpur | BNED | Remja-1 | TRL-2 | 2021-10-08 | 9 | 15 | Mr.Kandu Toppo SDO Belpahar | 2 | Line and PSS Maintenance | Jharuapada |  | No
67 | Sambalpur | BNED | Remja-1 | OPGC | 2021-10-09 | 9 | 15 | Mr.Kandu Toppo SDO Belpahar | 6 | Line and PSS Maintenance | OPGC,Bandhabahal,Pandri |  | No
68 | Sambalpur | BNED | Remja-1 | OPGC | 2021-10-18 | 9 | 15 | Mr.Kandu Toppo SDO Belpahar | 6 | Line and PSS Maintenance | OPGC,Bandhabahal,Pandri |  | No
69 | Sambalpur | DED | Rengali | Budhapal | 2021-10-09 | 8 | 14 | Mr.Anando kalo | 2 | Line and PSS Maintenance | Budhapal,Durga Industries |  | No
70 | Sambalpur | DED | Ambakata | Deogarh | 2021-10-16 | 8 | 14 | Mr.Anando kalo | 8 | Jumpering work And PSS Maintenance | Deogarh,Kandhal,Telioboni.Telimunda |  | No
71 | Sambalpur | Jharsuguda | Budhipadar | Airport | 2021-10-04 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 2 | Tree Trimming | Airport |  | No
72 | Sambalpur | Jharsuguda | Sarasmal | Sarbahal | 2021-10-05 | 10.00 AM | 12.00 PM | Bibeka nand Sarangi | 6 | Tree trimming and V cross arm alighment | Sarbahal |  | No
73 | Sambalpur | Jharsuguda | Khandokata | Laikera | 2021-10-06 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 5 | Tree Trimming and Pole straightening,Jumpring inside PSS | Laikera and Kirmira |  | No
74 | Sambalpur | Jharsuguda | Khandokata | Laikera | 2021-10-07 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 2 | Tree Trimming and Pole straightening,Jumpring inside PSS | Sodamal |  | No
75 | Sambalpur | Jharsuguda | Sarasmal | Kolabira | 2021-10-08 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 0 | Tree Trimming and PSS Maintenance | NA | No PSS will affect | No
76 | Sambalpur | Jharsuguda | Budhipadar | Industrial-1 | 2021-10-09 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 1 | Tree Trimming and PSS Maintenance | Sevenstar | No PSS will affect | No
77 | Sambalpur | Jharsuguda | Budhipadar | Industrial-1 | 2021-10-11 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 1 | Tree Trimming and PSS Maintenance | Allen Metalic | No PSS will affect | No
78 | Sambalpur | Jharsuguda | Budhipadar | Bagdihi | 2021-10-12 | 9.00 AM | 2.00 PM | Bibeka nand Sarangi | 4 | Tree Trimming and PSS Maintenance | Arda
79 | Sambalpur | Jharsuguda | Rajganpur | Kutra | 2021-10-04 | 10 | 15 | Tanuram Behera | 3 | Tree Trimming and PSS Maintenance | Garposh |  | No
80 | Sambalpur | Jharsuguda | Rajganpur | Kutra | 2021-10-05 | 10 | 14 | Tanuram Behera | 3 | AB Switch Installation | Garposh |  | No
81 | Sambalpur | Jharsuguda | Rajganpur | Kutra | 2021-10-08 | 10 | 14 | Tanuram Behera | 3 | Tree Trimming | Garposh |  | No
82 | Sambalpur | Jharsuguda | Khandokata | Hadipali | 2021-10-11 | 10 | 12 | Tanuram Behera | 4 | PSS Maintenance |  |  | No
83 | Sambalpur | Jharsuguda | Khandokata | Kuchinda | 2021-10-18 | 10 | 12 | Tanuram Behera | 6 | PSS Maintenance |  |  | No
84 | Sambalpur | Jharsuguda | Khandokata | Hadipali | 2021-10-19 | 10 | 12 | Tanuram Behera | 2 | PSS Maintenance |  |  | No
85 | Sambalpur | Jharsuguda | Sundergarh | Bamra | 2021-10-22 | 10 | 14 | Tanuram Behera | 2 | Tree Trimming |  |  | No
86 | Sambalpur | Jharsuguda | sundergarh | Bamra | 2021-10-23 | 10 | 14 | Tanuram Behera | 4 | Tree trimming |  |  | No
87 | Sambalpur | Jharsuguda | Khandokata | Hadipali | 2021-10-25 | 10 | 13 | Tanuram Behera | 4 | Fasimal PSS Maintenance |  |  | No
88 | Sambalpur | Jharsuguda | Khandokata | Hadipali | 2021-10-27 | 10 | 13 | Tanuram Behera | 4 | Tree Trimming |  |  | No
89 | Sambalpur | Jharsuguda | Khandokata | Hadipali | 2021-10-28 | 10 | 13 | Tanuram Behera | 4 | Line maintenance |  |  | No
90 | Sambalpur | Jharsuguda | Khandokata | Kuchinda | 2021-10-29 | 10 | 13 | Tanuram Behera | 6 | Line maintenance |  |  | No
91 | Sambalpur | Jharsuguda | Khandokata | kuchinda | 2021-10-30 | 10 | 13 | Tanuram Behera | 6 | Line maintenance |  |  | No
92 | SAMBALPUR | SEED | 132/33KV GSS GANESHNAGAR SBP | 33KV RENGALI(SBP) | 2021-10-04 | 9.00 AM | 3.00 PM | SDO,RENGALI | 6 MW | TREE TRIMMING, MAINTENANCE AND INSTALLATION OF ISOLATOR | SASON, MAJHIPALI,PRADHANPALI,GAMBHARKANTA,KULTANUAPALI,PARMANPUR,MURA,RASIAPLI,SERSUATAL,PANDRI,BHIKAMPUR |  | No
93 | SAMBALPUR | SEED | 220/132/33KV GSS LAPANGA | 33 KV KATARBAGA | 2021-10-05 | 9.00 AM | 3.00 PM | SDO,RENGALI | 4 MW | TREE TRIMMING & MAINTENANCE | KATARBAGA, GULAMAL, JHANKARPALI,TAMPERKELA |  | No
94 | SAMBALPUR | SEED | 132/33KV GSS KHANDAKATA | 33 KV LAIDA | 2021-10-07 | 9.00 AM | 3.00 PM | ESO LAIDA | 5 MW | TREE TRIMMING & MAINTENANCE | LAIDA, RENGLOI, KANTAPALI, GUCHAPALI, DALPATPALI, DEHERIPALI,MAGRAPALI, MARHAPATRA,KHUNTAMAL,KINALOI, BHAGIPALI, MAHADA, KENADHIPA, BINJIPALI, JUNADIHI, MANICKMUNDA, KHINDAPARA,FASIMAL, |  | No
95 | SAMBALPUR | SEED | 220/132/33KV GSS LAPANGA | 33 KV RENGALI | 2021-10-09 | 9.00 AM | 3.00 PM | SDO,RENGALI | 6 MW | TREE TRIMMING & MAINTENANCE | RENGALI,RAMPELLA,GANESHNAGAR,SALAD,NISHANBHANGA,RAMCHANDRANAGAR,JHARMUNDA,PONDLOI,GURUPALI |  | No
96 | ROURKELA | RAJGANGPUR | 132/33KV KALUNGA | 33KV IDC | 2021-10-22 | 10.00 AM | 1.00 PM | SDO,KALUNGA | 16 MW | Maintainance and Tree Trimmng | KALUNGA |  | NO
97 | ROURKELA | RAJGANGPUR | 132/33KV KALUNGA | 33KV KALUNGA | 2021-10-08 | 9.00 AM | 12.00 PM | SDO,KALUNGA | 8 MW | Maintainance and Tree Trimmng | KALUNGA |  | NO
98 | ROURKELA | RAJGANGPUR | 132/33KV KALUNGA | 33KV INDUSTRIAL | 2021-10-06 | 9.00 AM | 12.00 PM | SDO,KALUNGA | 12 MW | Maintainance and Tree Trimmng | KALUNGA |  | NO
99 | ROURKELA | RAJGANGPUR | 132/33KV KALUNGA | 33KV BALANDA | 2021-10-20 | 9.00 AM | 12.00 PM | SDO,KALUNGA | 2 MW | Maintainance and Tree Trimmng | GOTIDHARA |  | NO
100 | ROURKELA | RAJGANGPUR | 132/33KV CHHEND | 33KV VEDVYAS | 2021-10-04 | 8.00 AM | 4.00 PM | SDO,KALUNGA | 8 MW | Maintainance and Tree Trimmng | VEDVYAS |  | NO
101 | ROURKELA | RAJGANGPUR | 132/33KV CHHEND | 33KV KUARMUNDA INDUSTRIAL | 2021-10-04 | 8.00 AM | 4.00 PM | SDO,KUARMUNDA | 18 MW | Maintainance and Tree Trimmng | KUANRMUNDA |  | NO
102 | ROURKELA | RAJGANGPUR | 132/33KV CHHEND | 33KV BIRAMITRAPUR | 2021-10-04 | 8.00 AM | 4.00 PM | SDO,KUARMUNDA | 15 MW | Maintainance and Tree Trimmng | KUANRMUNDA |  | NO
103 | ROURKELA | RAJGANGPUR | 132/33KV CHHEND | 33KV PURUNAPANI | 2021-10-04 | 8.00 AM | 4.00 PM | SDO,KUARMUNDA | 12 MW | Maintainance and Tree Trimmng | HATIBARI |  | NO
104 | ROURKELA | RSED | 132/33KV ROURKELA | 33KV BONAI INDUSTRIAL | 2021-10-04 | 9.00 AM | 5.00PM | SDO,PANPOSH | 19MW | Maintainance and Tree Trimmng | Ideal Plant,Rexon,Jay Balaji plant |  | NO
105 | ROURKELA | RSED | 132/33KV ROURKELA | 33KV LATHIKATA | 2021-10-25 | 9.00 AM | 2.00PM | SDO,PANPOSH | 9MW | Maintainance and Tree Trimmng | LATHIKATA,JALDA |  | NO
106 | ROURKELA | RSED | 132/33KV ROURKELA | 33KV IDC | 2021-10-27 | 10.00 AM | 2.00PM | SDO,PANPOSH | 10MW | Maintainance and Tree Trimmng | PANPOSH,CIVIL TOWNSHIP,BALUGHAT |  | NO
107 | ROURKELA | RSED | 132/33KV CHHEND | 33KV CHHEND | 2021-10-04 | 9.00 AM | 5.00PM | SDO,INDUSTRIAL ESTATE | 11MW | Maintainance and Tree Trimmng | KALINGA BIHAR,PHASE -1,SELF FINANCE,LUHAKERA,RDA,PANPOSH |  | NO
108 | ROURKELA | RSED | 132/33KV ROURKELA | 33KV LATHIKATA | 2021-10-18 | 9.00 AM | 2.00PM | SDO,PANPOSH | 9MW | Maintainance and Tree Trimmng | LATHIKATA,JALDA |  | NO
109 | ROURKELA | SED | 132/33KV SANKARA | 33KV MAJHAPADA | 2021-10-01 | 8.00 AM | 4.00PM | SDO,SUNDARGARH | 3.5 MW | Maintainance and Tree Trimmng | GADIAJOR TO BHAWANIPUR |  | NO
110 | ROURKELA | RED | 132/33KV CHHEND | 33KV BASANTI | 2021-10-06 | 11.00 AM | 2.00 PM | SDO,BASANTI | 6.5MW | Maintainance and Tree Trimmng | DAV, PHD |  | NO
111 | ROURKELA | RED | 132/33 KV ROURKELA | 33KV GOPABANDHUPALI | 2021-10-24 | 10.00 AM | 1.00 PM | SDO,BASANTI | 2.5MW | Maintainance and Tree Trimmng | GB PALI, MS PALI, TIMBER COLONY |  | NO
112 | ROURKELA | RED | 132/33KV CHHEND | 33KV NIT | 2021-10-04 | 9.00 AM | 4.00 PM | SDO,KOELNAGAR | 10MW | Maintainance and Tree Trimmng | NIT CAMPUS,JAGDA,NAYABAZAR |  | YES
113 | ROURKELA | RED | 132/33KV CHHEND | 33KV KOELNAGAR | 2021-10-08 | 10.00 AM | 4.00 PM | SDO,KOELNAGAR | 7MW | Maintainance and Tree Trimmng | KOEL NAGAR, JHIRPANI |  | NO
114 | ROURKELA | RED | 132/33 KV ROURKELA | 33KV BONDAMUNDA | 2021-10-11 | 10.00 AM | 12.00 PM | SDO,BISRA | 4MW | Maintainance and Tree Trimmng | BONDOMUNDA, BALABHADRA MARKET |  | NO
115 | ROURKELA | RED | 132/33 KV ROURKELA | 33KV BONDAMUNDA | 2021-10-20 | 10.00 AM | 12.00 PM | SDO,BISRA | 4MW | Maintainance and Tree Trimmng | BONDOMUNDA, BALABHADRA MARKET |  | NO
116 | ROURKELA | RED | 132/33 KV CHHEND | 33KV BISRA | 2021-10-28 | 9.00 AM | 12.00 PM | SDO,BISRA | 7.5 MW | Maintainance and Tree Trimmng | DHADRI, BARSUAN, BISRA 1, BISRA 2, JAREIKELA, BAMBUA |  | NO
Note on D71: Author: Charged on dt.21.04.2017
Note on D75: Author: Charged on dt.21.04.2017

## OPTCL
Planned Outages Report For the Month of Oct 2021
From Date:- 01.10.2021 to 31.10.2021 OUTAGE REQUESTED ON ACCOUNT OF OPTCL
SL No. | Name of the Circle | Name of the Division | 220/132/33 KV GSS Name | Name of 33 KV O/G Feeder or Name of Equipment | Date of Outage | Isolation Time | Restoration Time | Name of Outage taken Person | Affected Load in MW | Reason of Outage | Key Areas Affected | Remarks | PRESS NOTE RELEASE REQUIREMENT (YES/NO)
1 | Sambapur | SED | Ganesh Nagar | Aithapali | 2021-10-04 | 8 | 16 | Mr. Jasmeet Chhabra SDO Ainthapali | 20 | Line and PSS Maintenance | Aithapali |  | No
2 | Sambapur | SEED | Rairakhol | Rairakhol | 2021-10-08 | 8 | 18 | Mr.Deepak Rout | 4 | Line and PSS Maintenance | Rairakhol |  | No
3 | Sambapur | SEED | Rairakhol | Naktideoul | 2021-10-08 | 8 | 18 | Mr.Deepak Rout | 3 | Line and PSS Maintenance | Rairakhol |  | No
4 | Sambalpur | BNED | Remja-1 | TRL-2 | 2021-10-01 | 8 | 16 | Mr.Kandu Toppo SDO Belpahar | 8 | Line and PSS Maintenance | Muchbahal,Dhulunda,Jharuapada |  | No
5 | Sambalpur | BNED | Remja-1 | Brajraj nagar | 2021-10-01 | 8 | 16 | SDO Brajrajraj nagar | 5 | Line and PSS Maintenance | Brajraj Nagar |  | No