## TPWODL
Planned Outages Report For the Month of MAY 2022
From Date:- 01-05-2022 to 31-05-2022 OUTAGE REQUESTED ON ACCOUNT OF TPWODL
SL No- | Name of the Circle | Name of the Division | 220/132/33kV GSS Name | Name of the 33kV feeder | Date of Outage | Isolation Time | Restoration Time | Name of Outage taken Person | Affected Load in MW | Reason of Outage | Key Areas Affected | Remarks | PRESS NOTE RELEASE REQUIREMENT (YES/NO)
1 | BOLANGIR | BED,Bolangir | Tusura | Tusura | 2022-05-01 | 6:00 | 10:00 | SDO Tusura | 12 | Tusura PSS Maintainace | Tusura,Gudvela,Arjunpur,Samara,Natraj,Mahala |  | NO
2 | BOLANGIR | TED, Titilagarh | Kantabanji | Industrial Feeder | 2022-05-01 | 8:00 | 10:00 | SDO Kantabanji | 5 | LA Installation | RP Rice Mill,Jaydurga Ginning,Pahadimata,OM Organic |  | NO
3 | KALAHANDI | KWED | 132/33 KV GSS Tentulikhunti | Makhiguda | 2022-05-02 | 9:00 | 14:30 | Mr. Pabiraj Majhi | 1 | Line Maintenance & Tree Trimming | Makhiguda, Mangalpur, Dhansuli, Mahulpatna | only Mukhiguda pss is under outage | NO
4 | KALAHANDI | KEED | 33/11kV Khariar PSS | Borda (Sindheikela) | 2022-05-03 | 8:30 | 13:00 | Mr. Sudhir Ku. Mohapatra | 2.5 | PSS Maintenance | Borda town, Seinpur, Artal, Mahaling | Outage taken for Only Borda PSS | NO
5 | KALAHANDI | KWED | 220/132/33 KV Baner GSS | Badkutru | 2022-05-03 | 9:00 | 14:30 | Mr. Kali Prasan Das | 0 | Line Maintenance & Tree Trimming | No area will be affected | No PSS under Outage | NO
6 | BARGARH | BWED, Bargarh | Ghenss 132/33KV GSS | 33KV Melchamunda (Ghenss GSS to Melchamunda PSS) | 2022-05-03 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 10 | PSS maintenance work | Melchamunda and Kundakhai PSS remain shutdown | Outage from GSS | NO
7 | BOLANGIR | BED,Bolangir | Barpalli | Melchamunda | 2022-05-04 | 7:00 | 9:00 | SDO Loisingha | 5 | Intermediate Pole Erection ,AB Switch Female Contact Change | Agalpur,Bharsuja |  | NO
8 | BOLANGIR | SED,SONEPUR | Sonepur | Dumerbahal | 2022-05-04 | 7:00 | 9:00 | SDO Sonepur | 12 | Tree Trimming,Jumper tightening | Hardokhol,Dumerbahal,Tarva |  | NO
9 | BOLANGIR | SED,SONEPUR | Barpalli | Pandikital | 2022-05-04 | 7:00 | 9:00 | SDO BINKA | 3.5 | Tree Trimming,V Cross Arm Straighetening,Pin Binding | Mayabara,Rampur,Badkarley |  | NO
10 | BOLANGIR | TED, Titilagarh | Kantabanji | Kantabanji | 2022-05-04 | 8:00 | 10:00 | SDO Kantabanji | 5 | LA Installation in Kantabanji PSS | Kantabanji Town,Ashrampada |  | NO
11 | KALAHANDI | KWED | 33/11kV Junagarh GSS | Kalampur | 2022-05-04 | 8:00 | 14:00 | Mr. S.S. Swain | 2 | Line & PSS Maintenance | Kalampu, Bankapala, Bandhakana, Th.Rampur, Gopalpur, Badchergaon, Adri, Gopinathpur, Maligaon etc. | Th.Rampur, Kalampur & Adri PSS under Outage | NO
12 | SAMBALPUR | SEED | 220/132/33KV LAPANGA | 33KV RENGALI-LPG | 2022-05-04 | 6:00 | 11:00 | SDO RENGALI | 7 | Line maintenance & PSS RENGALI | Rengali |  | NO
13 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Jamankira | 2022-05-04 | 8:00 | 12:00 | SDO KUCHINDA | 0.2 | Line Maintenance PSS Maintenance - Jamankira | jamankira |  | NO
14 | SAMBALPUR | BNED Brajrajnagar | Remja | 33KV TRL-2 | 2022-05-04 | 6:00 | 10:00 | SDO BELPAHAR | 0.6 | Line Maintenance PSS Maintenance -Mucchbahal | Belpahar nearby areas |  | NO
15 | SAMBALPUR | JED, Jharsuguda | Budhipadar | 33KV Industrial-1 | 2022-05-04 | 6:30 | 10:30 | SDO-2 JED | 1 | Line Maintenance | HT Industry-LN metallics |  | NO
16 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Gaisilet | 2022-05-04 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 7 | PSS maintenance work | Gaisilet,lebidi,firingimal,buromunda and talpali area | Outage from GSS | NO
17 | ROURKELA | RED RKL | 132/33KV CHHEND | 33KV NIT | 2022-05-04 | 9:00 | 11:00 | SDO,KOLENAGAR | 13 | Isolator Replacement & PSS Maintenance | KOLENAGAR,JHIRPANI,SHAKTINAGAR |  | NO
18 | ROURKELA | RED Rajgangpur | 132/33KV CHHEND | 33KV VEDVYAS (PARTLY TOWORDS ESTERN ) | 2022-05-04 | 8:00 | 13:00 | SDO,KALUNGA | 4 | Rejumpering Work ,Installation of Isolator | KALUNGA INDUSTRIALS |  | NO
19 | ROURKELA | SED | 132/33KV SANKARA | 33KV COLLEGE | 2022-05-04 | 7:30 | 10:00 | SDO,SUNDARGARH | 7 | PSS Maintenance & AB Switch Maintenance | College Area |  | NO
20 | BOLANGIR | BED,Bolangir | Tusura | Deogaon | 2022-05-05 | 7:00 | 9:00 | SDO Tusura | 3 | Deogaon PSS Maintainance | Deogaon,Gaibahal,Sagarpalli,Tusura |  | NO
21 | KALAHANDI | KWED | 33/11V Badkutru PSS | Charbahal | 2022-05-05 | 9:00 | 14:30 | Mr. Kali Prasan Das | 0 | Line Maintenance & Tree Trimming | No area will be affected | No PSS under Outage | NO
22 | KALAHANDI | NUAPADA | 132/33kV Bhera GSS | Bisora | 2022-05-05 | 8:00 | 11:00 | Mr. Pradipta Khilar | 5 | Line Maintenance & Tree Trimming | Bisora, Bhaleswar, Beltukuri, Saipala, Khairani, Darlimunda | Bisora & Saipala PSS under Outage | NO
23 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Kusumi | 2022-05-05 | 8:00 | 12:00 | SDO KUCHINDA | 0.1 | Line Maintenance PSS Maintenance -Kusumi | kusumi |  | NO
24 | SAMBALPUR | JED, Jharsuguda | SARASMAL | 33KV Airport(MEDICAL LINE) | 2022-05-05 | 6:30 | 10:30 | SDO-I JHARSUGUDA | 2 | Line Maintenance and PIN BINDING | MEDICAL PSS |  | NO
25 | BARGARH | BWED, Bargarh | Ghenss 132/33KV GSS | 33KV Padampur | 2022-05-05 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 6.5 | PSS maintenance work | Padampur PSS remain shutdown | Outage from GSS | NO
26 | BARGARH | BED, Bargarh | 132 / 33 KV GSS Katapali | 33KV Attabira | 2022-05-05 | 7:00 | 10:30 | Manmatha Nath Das (SDO of Attabira Sub-Division) | 26 | Maintenance work | Attabira,Patrapali,Thuapali and Bheden PSS remain shutdown. | Outage from GSS | NO
27 | ROURKELA | RED Rajgangpur | 132/33KV CHHEND | 33KV BIRAMITRAPUR | 2022-05-05 | 8:00 | 14:00 | SDO,KUARMUNDA | 12 | Rejumpering Work ,Feeder LA Installation, AB switch Installation | KUARMUNDA |  | NO
28 | ROURKELA | SED | 132/33KV SANKARA | 33KV KUNDUKELA | 2022-05-05 | 7:00 | 11:00 | SDO,SUNDARGARH | 2 | Tree Trimming & Isolator Maintenance | Kundukela Section |  | NO
29 | BOLANGIR | SED,SONEPUR | Sonepur | Dumerbahal | 2022-05-06 | 7:00 | 9:00 | SDO Sonepur | 4 | Jumper Tightness,Tree Triiming | Hardokhol,Dumerbahal,Tarva |  | NO
30 | BOLANGIR | BED,Bolangir | Laltikra | Boudh | 2022-05-06 | 7:00 | 9:00 | SDO Balangir-1 | 3.5 | Tree Trimming,AB Switch Repairing, | Power House,Sudapada,Balangir Jail |  | NO
31 | KALAHANDI | KWED | 33/11V Badkutru PSS | Charbahal | 2022-05-06 | 9:00 | 14:30 | Mr. Kali Prasan Das | 0 | Line Maintenance & Tree Trimming | No area will be affected | No PSS under Outage | NO
32 | KALAHANDI | NUAPADA | 132/33kV Bhera GSS | Khariar Road | 2022-05-06 | 8:00 | 11:00 | Mr. Pradipta Ku. Khilar | 5 | Line & PSS Maintenance | Nuapada Town, Sakhatora, Sarabong, Khariar Road Town, Patel Nagar, Biromal, Banka etc, | Only Kh. Road PSS under Outage | NO
33 | SAMBALPUR | SEED | 132/33KV MANESWAR | 33KV PADIABAHAL | 2022-05-06 | 7:00 | 12:00 | SDO DHANUPALI | 8 | Line maintenance & PSS PADIABAHAL,HERO | Padiabahal & Hero |  | NO
34 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Kesibahal | 2022-05-06 | 8:00 | 12:00 | SDO KUCHINDA | 0.2 | Line Maintenance PSS Maintenance -Kesibahal | kesibahal |  | NO
35 | SAMBALPUR | JED, Jharsuguda | Budhipadar | 33KV Industrial-1 | 2022-05-06 | 6:30 | 10:30 | SDO-2 JED | 1 | Line Maintenance | HT Industry-seven star |  | NO
36 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Lakhmara | 2022-05-06 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 3.5 | Tree trimming and pin insulator replacement work | Sambalpuri and Badikata area | Outage from GSS | NO
37 | ROURKELA | RSED RKL | 132/33KV ROURKELA | 33KV IDC | 2022-05-06 | 9:00 | 13:00 | SDO.PANPOSH | 10 | CT,PT installation at 33KV I/C Breaker | PANPOSH,CIVIL TOWNSHIP,JP HOSPITAL |  | NO
38 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV SUNDARGARH | 2022-05-06 | 7:00 | 12:00 | SDO,RAJGANGPUR NO -II | 12 | Tree trimming Disc ,Pin Insulator and V crossarm change and Re-jumpering | KUTRA INDUSTRIAL |  | NO
39 | ROURKELA | SED | 132/33KV SANKARA | 33KV SUBDEGA | 2022-05-06 | 7:00 | 11:00 | SDO,SUNDARGARH | 8 | Tree Trimming, Pin Insulator Replacement, V-Cross Arm Straighteening | Subdega, Balisankara,Karamdihi |  | NO
40 | BOLANGIR | SED,SONEPUR | Sonepur | Binka | 2022-05-07 | 6:00 | 9:00 | SDO Binka | 12 | Tree Trimming,AB Switch Repairing | Saledi,Binka,Bisalpalli,Headtikra |  | NO
41 | KALAHANDI | NUAPADA | 33/11kV Nuapada PSS | Sarabong | 2022-05-07 | 8:00 | 13:00 | Mr. Bholanath Naik | 2.5 | Line Maintenance | Dharmabandha, Sarabong, Bhainsmundi | Only Sarabong PSS under Outage | NO
42 | SAMBALPUR | SED | GANESH NAGAR | 33KV CHERUAPADA | 2022-05-07 | 8:00 | 12:00 | SDO 2 SBP | 10 | Line MAINTANANCE PSS-CHERUAPADA,BADBAZAR, | Cheruapada,Bad bazaar,Vikash Hospital, |  | YES
43 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Jamankira | 2022-05-07 | 8:00 | 12:00 | SDO KUCHINDA | 0.4 | Line Maintenance PSS Maintenance -Jamankira | Jamankira |  | NO
44 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Paikmal (Padampur GSS to Paikmal PSS) | 2022-05-07 | 7:00 | 12:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 19.6 | 33KV ISO's male contact replacement work at Jhankarpada(Near Padampur GSS) | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
45 | ROURKELA | RED RKL | 132/33KV CHHEND | 33KV KOLENAGAR | 2022-05-07 | 10:00 | 11:30 | SDO,KOLENAGAR | 10 | 33KV Bay Maintenance & Isolator Maintenance | KOLENAGAR,JHIRPANI,SHAKTINAGAR |  | NO
46 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV SUNDARGARH (ALANDA) | 2022-05-07 | 8:00 | 14:00 | SDO,RAJGANGPUR NO -I | 4 | Tree Trimming/ Alanda PSS Maintenance | ALANDA AREAS |  | NO
47 | ROURKELA | SED | 132/33KV BRAJARAJNAGAR | 33KV AYRAN | 2022-05-07 | 6:00 | 10:00 | SDO,UJALPUR | 2 | Tree trimming & Pin insulator Replacement | ACB India,Beleimunda & Hemgiri Section |  | NO
48 | BOLANGIR | BED,Bolangir | Laltikra | Dunguripalli | 2022-05-08 | 6:00 | 9:00 | SDO Binka | 4 | Tree Trimming,V -Cross Arm Straightening,Pin Insulator Replacement | Shankar Rice Mill,Minerva,Prem Disposal,Lalita Plastic |  | NO
49 | BOLANGIR | TED, Titilagarh | Patnagarh(Rampur) | Khaprakhol | 2022-05-08 | 8:00 | 10:00 | SDO Patnagarh | 4.5 | Line Maintainance(V-Cross Arm Straightening) | Patnagarh,Thakpada,Khaprakhol,Lathore |  | NO
50 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Paikmal (Padampur GSS to Paikmal PSS) | 2022-05-08 | 7:00 | 12:00 | Purandar sahu (SDO of Paikmal Sub-Division) | 19.6 | 33KV ISO's male contact replacement work at Jhankarpada(Near Padampur GSS) | PSS Affected- Paikmal, Mandosil, Jhitki, Jharbandh, Dava, Dungripali | Outage from Paikmal PSS | NO
51 | ROURKELA | RED RKL | 132/33KV CHHEND | 33KV BASANTI | 2022-05-08 | 08.00 AM | 11:00 | SDO,BASANTI | 0 | Tree Trimming & PSS Yard Cleaning | DAV,PHD AREA | Load Diverted from Pilot Project Feeder | NO
52 | ROURKELA | SED | 132/33KV SANKARA | 33KV MAJHAPADA | 2022-05-08 | 7:00 | 11:00 | SDO,SUNDARGARH | 3 | Pin Insulator Replacement, Straighteening of V-Cross Arm | Majhapada Section |  | NO
53 | KALAHANDI | KWED | 132/33 KV Tentulikhunti GSS | Mukhiguda | 2022-05-09 | 9:00 | 14:30 | Mr. Pabiraj Majhi | 1 | Line Maintenance & Tree Trimming | Makhiguda, Mangalpur, Dhansuli, Mahulpatna | only makhiguda pss is under outage | NO
54 | BARGARH | BWED, Bargarh | Ghenss 132/33KV GSS | 33KV Melchamunda (Melchamunda PSS to Kundakhai PSS) | 2022-05-09 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 2.8 | PSS maintenance work | Kundakhai and Jamutpali area | Outage from GSS | NO
55 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV KUTRA | 2022-05-09 | 7:00 | 12:00 | SDO,RAJGANGPUR NO -II | 15 | Disc ,Pin Insulator and V-Cross Arm Replacement | KUTRA INDUSTRIAL |  | NO
56 | ROURKELA | SED | 132/33KV BRAJARAJNAGAR | 33KV ARYAN | 2022-05-09 | 6:00 | 10:00 | SDO,UJALPUR | 2 | Isolator Maintenance & Tree trimming | ACB India,Beleimunda & Hemgiri Section |  | NO
57 | BOLANGIR | BED,Bolangir | Barpalli | Melchamunda | 2022-05-10 | 7:00 | 9:00 | SDO Loisingha | 5 | 5 nos V-Cross Arm Straightening,Tree Trimming | Agalpur,Bharsuja |  | NO
58 | KALAHANDI | KEED | 132/33kV Kesinga GSS | Bhawanipatna No.1 | 2022-05-10 | 8:00 | 13:00 | Mr. Ajit Sahu | 3.5 | Feeder Maintenance | Utkela, Kundabandh, Pastikudi, Karlapada | Karlapada & Utkela PSS under Outage | NO
59 | KALAHANDI | KWED | 33/11kV Junagarh PSS | Th. Rampur | 2022-05-10 | 8:00 | 14:00 | Mr. S.S. Swain | 1.2 | Line & PSS Maintenance | Dumerpadar, Badchatarang, Gopalpur, Th.Rampur, Adri, Dalguda, Gopinathpur etc | Th. Rampur & Adri PSS under Outage | NO
60 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Bamara | 2022-05-10 | 9:00 | 12:00 | SDO KUCHINDA | 0.1 | Line Maintenance PSS Maintenance -Bamra | Bamra |  | NO
61 | SAMBALPUR | BNED Brajrajnagar | Remja | 33KV TRL-2 | 2022-05-10 | 8:00 | 12:00 | SDO BELPAHAR | 0.6 | Line Maintenance PSS Maintenance -Mucchbahal | Belpahar nearby areas |  | NO
62 | SAMBALPUR | JED, Jharsuguda | Budhipadar | 33KV Bagdihi | 2022-05-10 | 6:30 | 10:30 | SDO-I JHARSUGUDA | 2.5 | Line Maintenance,PIN BINDING,v-cross arm straightening | ARDA PSS |  | NO
63 | ROURKELA | RED Rajgangpur | 132/33KV CHHEND | 33KV KUARMUNDA INDUSTRIAL | 2022-05-10 | 7:00 | 14:00 | SDO,KUARMUNDA | 15 | Rejumpering Work ,Feeder LA Installation, Pin Insulator Replacement | KUARMUNDA INDUSTRIAL AREA |  | NO
64 | ROURKELA | SED | 132/33KV BRAJARAJNAGAR | 33KV SARGIPALI | 2022-05-10 | 6:00 | 10:00 | SDO,UJALPUR | 12 | Tree Trimming, Pin Insulator Replacement, V-Cross Arm Straighteening | Sargipali,Grajanbahal,Mangaspur,Tumapali |  | NO
65 | KALAHANDI | NUAPADA | 132/33kV Bhera GSS | Bisora | 2022-05-11 | 8:00 | 11:00 | Mr. Pradipta Khilar | 5 | Line Maintenance & Tree Trimming | Bisora, Bhaleswar, Beltukuri, Saipala, Khairani, Darlimunda | Bisora & Saipala PSS under Outage | NO
66 | SAMBALPUR | SEED | 132/33 KV CHIPLIMA | 33KV DHAMA-1 | 2022-05-11 | 7:00 | 12:00 | SDO DHANUPALI | 12 | Line maintenance & PSS DHAMA,HATIBARI,JUJOMURA,GUNDERPUR | Dhama,Hatibari,Jujomura,Gunderpur |  | NO
67 | SAMBALPUR | SED | GANESH NAGAR | 33KV AINTHAPALI | 2022-05-11 | 7:00 | 11:00 | SDO AINTHAPALI | 30 | Line MAINTANANCE PSS-AINTHAPALI | Bareipali,Ainthapali,Budharaja,GM College Area |  | YES
68 | SAMBALPUR | BNED Brajrajnagar | Remja | 33KV Brajarajnagar | 2022-05-11 | 8:00 | 12:00 | SDO BRAJARAJNAGAR | 0.3 | Line Maintenance PSS Maintenance -Brajrajnagar | Brajarajnagar areas |  | NO
69 | SAMBALPUR | JED, Jharsuguda | Budhipadar | 33KV Industrial-1 | 2022-05-11 | 6:30 | 10:30 | SDO-2 JED | 7 | Line Maintenance PSS Maintenance | Badmal,LN Metallics ,Ankita industries,Seven Star |  | NO
70 | BARGARH | BED, Bargarh | 132 / 33 KV GSS Chiplima | 33KV Mahulpali | 2022-05-11 | 7:00 | 11:00 | Pradipta Sarangi (SDO of Bheden Sub-division) | 4 | Maintenance work | Dhatukpali and Gondturum (Mahulpali) PSS remain shutdown. | Outage from GSS | NO
71 | ROURKELA | RED Rajgangpur | 132/33KV CHHEND | 33KV PURNAPANI O/G (HATIBARI TO NUAGOAN) | 2022-05-11 | 9:00 | 14:00 | SDO,KUARMUNDA | 18 | Rejumpering Work ,Pin Insulator | NUAGOAN |  | NO
72 | ROURKELA | SED | 132/33KV SANKARA | 33KV SUBDEGA | 2022-05-11 | 7:00 | 11:30 | SDO,SUNDARGARH | 8 | Tree Trimming & PSS Maintenance | Subdega, Balisankara,Karamdihi |  | NO
73 | KALAHANDI | KEED | 132/33kV Kesinga GSS | Bhawanipatna No.2 | 2022-05-12 | 8:00 | 13:00 | Mr. Ajit Sahu | 1 | Feeder Maintenance | Consumers- Airstrip (Utkela), Baishali Water Industry, Basudev Foods, Radio Station | only HTC under Outage | NO
74 | KALAHANDI | KEED | 132/33kV Kesinga GSS | Belgaon | 2022-05-12 | 8:30 | 13:00 | Mr. Amiya Ranjan Panda | 5 | Line Maintenance | Karlamunda, Nunmath, Sisakhal | Nunmath, Sisakhal PSSs under Outage | NO
75 | SAMBALPUR | JED, Jharsuguda | Budhipadar | 33KV Bagdihi | 2022-05-12 | 6:30 | 10:30 | SDO-I JHARSUGUDA | 2.5 | Line Maintenance,PIN BINDING,v-cross arm straightening | BAGDIHI PSS |  | NO
76 | ROURKELA | RSED RKL | 132/33KV ROURKELA | 33KV LATHIKATA | 2022-05-12 | 8:00 | 12:00 | SDO.PANPOSH | 9 | Pole Straighteening | LATHIKATA,RAMJODI,SUIDIHI |  | NO
77 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV PURUNAPANI O/G | 2022-05-12 | 7:00 | 14:00 | SDO,KUARMUNDA | 12 | Rejumpering Work , Disc and Pin Insulator Replacement | HATIBARI AND NUAGAON |  | NO
78 | BOLANGIR | BED,Bolangir | Barpalli | Melchamunda | 2022-05-13 | 7:00 | 9:00 | SDO Loisingha | 5 | Pin Insulator replacement,Conductor Sagging 3 Span | Agalpur,Bharsuja |  | NO
79 | KALAHANDI | NUAPADA | 132/33kV Bhera GSS | Khariar Road | 2022-05-13 | 8:00 | 11:00 | Mr. Pradipta Ku. Khilar | 5 | Line AB Switch maintenance & tree trimming | Nuapada Town, Sakhatora, Sarabong, Khariar Road Town, Patel Nagar, Biromal, Banka etc, | Only Kh. Road PSS under Outage | NO
80 | SAMBALPUR | SED | KANTAPALI | 33KV GOSALA | 2022-05-13 | 8:00 | 12:00 | SDO HIRAKUD | 16 | Line MAINTANANCE PSS-GOSALA | GOSALA/CHIPLIMA/GODBHAGA |  | NO
81 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Kusumi | 2022-05-13 | 8:00 | 12:00 | SDO KUCHINDA | 0.1 | Line Maintenance PSS Maintenance -Kusumi | Kusumi |  | NO
82 | SAMBALPUR | JED, Jharsuguda | Khandokata | 33KV LAIKERA | 2022-05-13 | 6:30 | 10:30 | SDO-2 JED | 2 | Line Maintenance PSS-SODAMAL | Sodamal |  | NO
83 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Gaisilet | 2022-05-13 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 7 | PSS maintenance work | Gaisilet,lebidi,firingimal,buromunda and talpali area | Outage from GSS | NO
84 | ROURKELA | RSED RKL | 220/33KV BONAI | 33KV BONAI | 2022-05-13 | 8:00 | 12:00 | SDO,BONAI | 6 | Pin Insulator Replacement, Straighteening of V-Cross Arm,Tree Trimming | BONAI BLOCK AREA |  | NO
85 | ROURKELA | RED Rajgangpur | 132/33KV RAJGANGPUR | 33KV ROURKELA -1 | 2022-05-13 | 8:00 | 14:00 | SDO,RAJGANGPUR NO-I & SDO,KALUNGA | 20 | Tree Trimming ,Pin Insulator and Rejumpering Work, | BELEIGARH,KANSHBAHAL,KALUNGA, BHOGATOLA |  | NO
86 | BOLANGIR | BED,Bolangir | Laltikra | Barpalli | 2022-05-14 | 7:00 | 9:00 | SDO Loisingha | 4 | Tree Trimming,DISC Insulator Replacement,Loisingha PSS LA Replacement | Chattamakhna,Bhadra,Loisingha,Salveta |  | NO
87 | SAMBALPUR | SEED | 132/33KV KHANDOKATA | 33KV KUCHINDA(LAIDA) | 2022-05-14 | 7:00 | 12:00 | SDO RENGALI | 2 | Line maintenance & PSS LAIDA | Laida |  | NO
88 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Kuchinda | 2022-05-14 | 8:00 | 12:00 | SDO KUCHINDA | 0.1 | Line Maintenance PSS Maintenance -Kuchinda | Kuchinda |  | NO
89 | SAMBALPUR | JED, Jharsuguda | Khandokata | 33KV LAIKERA | 2022-05-15 | 6:30 | 11:00 | SDO-2 JED | 7 | Line Maintenance | SODAMAL,LAIKERA ,KIRMIRA |  | NO
90 | SAMBALPUR | DED | AMBAKATA | 33KV DEOGARH | 2022-05-15 | 7:00 | 12:00 | SDO DEOGARH | 5 | Line Maintenance | Reamal ,Telimunda,Satabara |  | NO
91 | ROURKELA | RED RKL | 33/11KV NIT | 33KV BISRA | 2022-05-15 | 8:00 | 12:00 | SDO,BISRA | 4.5 | PSS Maintenance & AB Switch Maintenance | BISRA,JAREIKALA |  | NO
92 | BOLANGIR | BED,Bolangir | Tusura | Deogaon | 2022-05-16 | 6:00 | 10:00 | SDO Tusura | 3 | Tree Trimming,Jumper Tightness | Jarasingha,Deogaon,Budhabahl,Kudasingha |  | NO
93 | KALAHANDI | NUAPADA | 33/11kV Komna PSS | Kurumpuri | 2022-05-16 | 8:00 | 13:00 | Mr. Bholanath Naik | 3 | Line Maintenance & Tree Trimming | Tarbod, Lakhna, Silati, JNV, Bhela | Only Kurumpuri PSS under Outage | NO
94 | ROURKELA | RSED RKL | 220/33KV BONAI | 33KV BONAI(GURUNDIA) | 2022-05-16 | 8:00 | 12:00 | SDO,BONAI | 2 | Pin Insulator Replacement,V-Cross arm straighteening | GURUNDIA BLOCK AREA |  | NO
95 | KALAHANDI | KWED | 132/33 KV Tentulikhunti GSS | Mukhiguda | 2022-05-17 | 9:00 | 14:30 | Mr. Pabiraj Majhi | 1 | Line Maintenance & Tree Trimming | Makhiguda, Mangalpur, Dhansuli, Mahulpatna | only makhiguda pss is under outage | NO
96 | SAMBALPUR | SED | KANTAPALI | 33 KV CHAURPUR | 2022-05-17 | 8:00 | 12:00 | SDO HIRAKUD | 6 | Line MAINTANANCE PSS-CHOURPUR | Chourpur,BR Steel |  | NO
97 | SAMBALPUR | JED, Jharsuguda | SARASMAL | 33KV KOLABIRA | 2022-05-17 | 6:30 | 10:30 | SDO-I JHARSUGUDA | 2 | Line Maintenance,PIN BINDING,v-cross arm straightening | PURNA PSS |  | NO
98 | KALAHANDI | NUAPADA | 132/33kV Bhera GSS | Bisora | 2022-05-18 | 8:00 | 11:00 | Mr. Pradipta Khilar | 3 | Line Maintenance & Tree Trimming | Bisora, Bhaleswar, Beltukuri, Saipala, Khairani, Darlimunda | Only Bisora PSS under Outage | NO
99 | SAMBALPUR | SED | GANESH NAGAR | 33KV CHERUAPADA | 2022-05-18 | 8:00 | 12:00 | SDO 2 SBP | 10 | Line MAINTANANCE PSS-CHERUAPADA,BADBAZAR, | Cheruapada,Bad bazaar,Vikash Hospital, |  | YES
100 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Kesiabahal | 2022-05-18 | 9:00 | 12:00 | SDO KUCHINDA | 0.1 | Line Maintenance PSS Maintenance -Kesibahal | Kesiabahal |  | NO
101 | ROURKELA | RSED RKL | 220/33KV BONAI | 33KV BONAI(INDUSTRY) | 2022-05-18 | 8:00 | 16:00 | SDO,BONAI | 8 | Pin Insulator Replacement, Straighteening of V-Cross Arm | INDUSTRIAL AREA |  | NO
102 | SAMBALPUR | JED, Jharsuguda | SARASMAL | 33KV KOLABIRA | 2022-05-19 | 6:30 | 10:30 | SDO-I JHARSUGUDA | 2 | Line Maintenance, PIN BINDING,v-cross arm straightening | PURNA PSS |  | NO
103 | KALAHANDI | KWED | 33/11kV Th.Rampur PSS | Adri | 2022-05-20 | 8:00 | 14:00 | Mr. S.S. Swain | 0.6 | Line & PSS Maintenance | Gopinathpur, Maligaon, Adri & Dalguda | Only Adri PSS under Outage | NO
104 | KALAHANDI | KWED | 220/132/33kV Baner GSS | Ladugaon | 2022-05-20 | 9:00 | 14:30 | Mr. B M Dalei | 0 | Line Maintenance, Tree Trimming & double jumpering at 3 locations | No area will be affected | No PSS under Outage | NO
105 | SAMBALPUR | SED | KANTAPALI | 33KV HIRAKUD | 2022-05-20 | 8:00 | 12:00 | SDO HIRAKUD | 6 | Line MAINTANANCE PSS-HIRAKUD | BOTH HIRAKUD URBAN & RURAL AREA |  | NO
106 | ROURKELA | RSED RKL | 220/33KV BARKOT | 33KV MAHULIDIHA | 2022-05-20 | 8:00 | 16:00 | SDO,BONAI | 2 | Tree Trimming,PSS Maintenance | MAHULIDIHA,KHANDADHRA,KULIPOSH,BADGAON |  | NO
107 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Jamankira | 2022-05-21 | 8:00 | 12:00 | SDO KUCHINDA | 0.1 | Line Maintenance PSS Maintenance -Jamankira | jamankira |  | NO
108 | SAMBALPUR | DEOGARH | RENGALI OPTCL | 33KV BUDHAPAL | 2022-05-21 | 7:00 | 12:00 | SDO DEOGARH | 1.5 | Line Maintenance PSS-BUDHAPAL | Budhapal,kundeigola |  | NO
109 | BARGARH | BWED, Bargarh | Ghenss 132/33KV GSS | 33KV Melchamunda (Ghenss GSS to Melchamunda PSS) | 2022-05-21 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 10 | PSS maintenance work | Melchamunda and Kundakhai PSS remain shutdown | Outage from GSS | NO
110 | ROURKELA | RSED RKL | 220/33KV BONAI | 33KV RAJAMUNDA(INDUSTRY) | 2022-05-21 | 8:00 | 16:00 | SDO,BONAI | 6 | Pin Insulator Replacement, Straighteening of V-Cross Arm | INDUSTRIAL AREA |  | NO
111 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Dahita | 2022-05-22 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 2 | Tree trimming and pin insulator replacement work | Dahita PSS remain shutdown | Outage from GSS | NO
112 | KALAHANDI | KWED | 220/132/33kV Baner GSS | Gadramal (Ladugaon) | 2022-05-23 | 9:00 | 14:30 | Mr. B M Dalei | 5 | Tree Trimming & isolator installation | Gadramal, Koksara, Dangriguda, Phubgaon, Temra & Majhiguda | Gadramal & Temra PSS under Outage | NO
113 | BARGARH | BED, Bargarh | Pradhanpali 132/33KV GSS | 33KV Tora | 2022-05-23 | 7:00 | 12:00 | Bijay Tiwary (SDO of Bargarh-2 Sub-Division) | 6 | Tree trimming work | 11KV Remunda,Tora,Sugarmill and Gaisima feeder | Outage from GSS | NO
114 | BARGARH | BWED, Bargarh | Padampur 132/33KV GSS | 33KV Lakhmara | 2022-05-23 | 7:00 | 12:00 | Sujit Behera (SDO of Padampur Sub-Division) | 3.5 | Tree trimming and pin insulator replacement work | Sambalpuri and Badikata area | Outage from GSS | NO
115 | KALAHANDI | KWED | 132/33 KV Tentulikhunti GSS | Mukhiguda | 2022-05-25 | 9:00 | 14:30 | Mr. Pabiraj Majhi | 1 | Line Maintenance & Tree Trimming | Makhiguda, Mangalpur, Dhansuli, Mahulpatna | only makhiguda pss is under outage | NO
116 | KALAHANDI | NUAPADA | 132/33kV Bhera GSS | Bisora | 2022-05-25 | 8:00 | 11:00 | Mr. Pradipta Khilar | 3 | Line Maintenance & Tree Trimming | Bisora, Bhaleswar, Beltukuri, Saipala, Khairani, Darlimunda | Only Bisora PSS under Outage | NO
117 | SAMBALPUR | JED, Jharsuguda | Khandakota | 33KV Jamankira | 2022-05-25 | 8:00 | 11:00 | SDO KUCHINDA | 0.4 | Line Maintenance PSS Maintenance -Jamankira | Jamankira |  | NO
118 | SAMBALPUR | BNED Brajrajnagar | Remja | 33KV TRL-2 | 2022-05-25 | 8:00 | 12:00 | SDO BELPAHAR | 0.6 | Line Maintenance PSS Maintenance -Mucchbahal | Belpahar nearby areas |  | NO
119 | BARGARH | BED, Bargarh | 132 / 33 KV GSS Katapali | 33KV Attabira | 2022-05-25 | 7:00 | 10:30 | Manmatha Nath Das (SDO of Attabira Sub-Division) | 26 | Maintenance work | Attabira,Patrapali,Thuapali and Bheden PSS remain shutdown. | Outage from GSS | NO
120 | KALAHANDI | KEED | 132/33kV Kesinga GSS | Belgaon | 2022-05-26 | 8:30 | 13:00 | Mr. Amiya Ranjan Panda | 5 | Line Maintenance | Karlamunda, Nunmath, Sisakhal | Nunmath, Sisakhal PSSs under Outage | NO
121 | ROURKELA | RSED RKL | 220/33KV JODA | 33KV JODA-TENSA | 2022-05-26 | 8:00 | 16:00 | SDO,BONAI | 9 | Maintainance and Tree Trimmng | KOIRA,TENSA & INDUSTRIAL AREA |  | NO
122 | BARGARH | BED, Bargarh | 132 / 33 KV GSS Chiplima | 33KV Khuntlipali | 2022-05-27 | 7:00 | 11:00 | Pradipta Sarangi (SDO of Bheden Sub-division) | 12 | Maintenance work | Khuntulipali PSS remain shutdown. | Outage from GSS | NO
123 | SAMBALPUR | DEOGARH | AMBAKATA | 33KV DEOGARH | 2022-05-28 | 7:00 | 12:00 | SDO DEOGARH | 12 | Line Maintenance PSS-KANDHAL,DEOGARH,TILEIBANI,RENGALBEDA,TELIMUNDA | KANDHAL,DEOGARH,TILEIBANI,RENGALBEDA,TELIMUNDA |  | NO
124 | ROURKELA | RED Rajgangpur | 132/33KV SUNDARGARH | 33KV BARGAON | 14-05--2022 | 8:00 | 14:00 | SDO,RAJGANGPUR NO -II | 5 | Tree trimming, Re-jumpering ,Pin Insulator Replacement | JARANGLOI |  | NO

## Master (hidden)
Circle | Circle | Division | SAMBALPUR | ROURKELA | KALAHANDI | BOLANGIR | BARGARH | Start Date | End Date | Start Time | End Time
SAMBALPUR | SAMBALPUR | SED | SED | RED RKL | KEED | BED,Bolangir | BED, Bargarh | 2021-01-01 | 2030-12-31 | 0:00 | 24:00 PM
ROURKELA | SAMBALPUR | SEED | SEED | RSED RKL | KWED | TED, Titilagarh | BWED, Bargarh
KALAHANDI | SAMBALPUR | JED, Jharsuguda | JED, Jharsuguda | RED Rajgangpur | NUAPADA | SED,SONEPUR
BOLANGIR | SAMBALPUR | BNED Brajrajnagar | BNED Brajrajnagar | SED
BARGARH | SAMBALPUR | DEOGARH | DEOGARH
| ROURKELA | RED RKL
| ROURKELA | RSED RKL
| ROURKELA | RED Rajgangpur
| ROURKELA | SED
| KALAHANDI | KEED
| KALAHANDI | KWED
| KALAHANDI | NUAPADA
| BOLANGIR | BED,Bolangir
| BOLANGIR | TED, Titilagarh
| BOLANGIR | SED,SONEPUR
| BARGARH | BED, Bargarh
| BARGARH | BWED, Bargarh

## OPTCL
Planned Outages Report For the Month of MAY 2022
From Date:- 01.05.2022 to 31.05.2022 OUTAGE REQUESTED ON ACCOUNT OF OPTCL
SL No. | Name of the Circle | Name of the Division | 220/132/33 KV GSS Name | Name of 33 KV O/G Feeder or Name of Equipment | Date of Outage | Isolation Time | Restoration Time | Name of Outage taken Person | Affected Load in MW | Reason of Outage | Key Areas Affected | Remarks | PRESS NOTE RELEASE REQUIREMENT (YES/NO)